## status_vs_resolution_status
status | resolution_status
in_analysis
Architecture change eliminated root cause. /classify returns specialty codes (no summary text), /search returns DB results. LLM never sees or summarizes provider results. strip_llm_summary function also added as defense-in-depth. Closed 2026-04-10. | tested_passed
closed_reqs_reorganized
Rule text already says BUG FIXED. Closed 2026-04-10. | tested_passed
in_analysis
in_analysis
in_analysis
tested_passed
in_analysis
testing
in_analysis
in_analysis
testing
failed_ist_testing
in_analysis
in_analysis
in_analysis
in_analysis
in_analysis
in_analysis
Fixed in FindCareApp.tsx refactor. Filter list div uses flex:1 + overflowY:auto (line 287). No max-height constraint. Closed 2026-04-10. | closed_reqs_reorganized
Rule text says PASS. Human signed off functionality for alpha. Closed 2026-04-10. | closed_reqs_reorganized
testing
Rule text says PASS. Human signed off for alpha. Closed 2026-04-10. | tested_passed
Rule text already says BUG FIXED. Closed 2026-04-10. | tested_passed
Rule text already says BUG FIXED. Closed 2026-04-10. | closed_reqs_reorganized
in_analysis
in_analysis
in_analysis
in_analysis
in_analysis
in_analysis
in_analysis
in_analysis
in_analysis
in_analysis
in_analysis
Not a bug â€” tokens display correctly. Smoke test had stale selectors and per-test page isolation. Fixed smoke test to use shared page fixture. UAT passed by Skip with screenshots 2026-04-10. | tested_passed
in_analysis
closed_reqs_reorganized
Deferred to Beta. HF Spaces does not support mTLS. Plan: Private Spaces + HF bearer token + signed session token. HF is the authority for transport auth. | in_analysis
in_analysis
tested_passed
in_analysis
Refactoring to shared React component library: Code/Shared/ux/ with typed components, hooks, and clean postMessage bus. GUIManager.tsx becomes thin consumer. | tested_passed
Verified FindCareApp.tsx line 81-82: selectedRef syncs from selection.state.selected. ChatWindow.tsx line 230-244: evaluate callback sends selectedRef.current. Closed 2026-04-10. | tested_passed
in_analysis
Verified main.py evaluate_proxy (line 541-577): mTLS certs configured correctly. Gemini removed (GPT-4.1 switch). Local uses findcare.crt/key + ca.crt via Caddy :8081. Closed 2026-04-10. | tested_passed
Same root cause as BUG-EVAL-002. selectedRef.current now syncs from selection.state.selected. Closed 2026-04-10. | tested_passed
tested_passed
Switched from Gemini 2.5 Flash to GPT-4.1. Verified main.py /classify endpoint uses CHAT_MODEL defaulting to gpt-4.1. Closed 2026-04-10. | tested_passed
Fixed tonight in index.html (only visible checked codes sent) and FindCareApp.tsx. Closed 2026-04-10. | closed_reqs_reorganized
deferred
fixing
fixing
tested_passed
Verified FindCareApp.tsx: timer clears after fetchProviders (line 168-169), comment on line 167 confirms intent. Also clears on error (line 182-183). Closed 2026-04-10. | tested_passed
fixing
fixing
fixing
fixing
fixing
fixing
fixing
fixing
fixing
fixing
fixing
fixing
fixing
closed_reqs_reorganized
closed_reqs_reorganized
closed_reqs_reorganized
closed_reqs_reorganized
closed_reqs_reorganized
fixing
fixing
fixing
fixing
fixing
fixing
fixing
fixing
fixing
fixing
fixing
fixing
fixing
fixing
fixing
fixing
in_analysis
in_analysis
in_analysis
in_analysis
fixing
in_analysis
fixing
testing
in_analysis
fixed
fixing
in_analysis
fixed
in_analysis
deferred
fixed
ist_working
fixing
ist_testing
in_analysis
fixing
in_analysis
fixed
fixed
fixing
new
new
new
Add TestStep15b (e.g., test_evalcare_rejects_without_client_cert) that attempts socket connection WITHOUT ctx.load_cert_chain and asserts the handshake fails. Add matching TestStep27b for SharedServices. Both the existing positive and the new negative tests must pass for mTLS enforcement to be claimed. Keep tests hardcoded to localhost:8001/8002 for now; env-parameterization of the mTLS steps is a separate refactor. | new
Read Code/Shared/session_token.py and every code path that mints tokens, tracing what runs on HF vs local. Diff the HF Dockerfile + requirements.txt vs the local environment — verify no module or dependency is missing that the minter needs. Inventory which files are copied by deploy-findcare-backend.yml vs what deploy_localhost.sh uses — mismatch is Skip's primary hypothesis for why the same codebase behaves differently. Fix the minter (or its packaging) so dev emits the full token format. Do NOT fix this by teaching the display parser to read short tokens; that would mask the security regression. Add a smoke-test assertion that the token emitted by each environment is well-formed (len >= 68, parseable into nonce + guid). | new
Bump step removed from all three HF deploy workflows (deploy-findcare/evaluatecare/shared). Build no longer increments on deploy. Pre-commit hook continues to bump on non-deploy commits per REQ-016. | tested_passed
Not a bug under DEVOPS-DEPLOY-001-REQ-016 (approved 2026-04-17). The post-commit hook incrementing build on each code-or-config commit is the correct enforcement mechanism. Claude's earlier neutering of the hook was incorrect and will be reverted. | removed
deploy_localhost_docker.sh now builds each backend as a Docker image from its Dockerfile + requirements.txt and runs as a container. No ambient-venv imports possible. Verified: local stack comes up green with the Docker path. | tested_passed
FindCare deploy workflow now preserves README.md on each push (cp /tmp, find -delete, cp back). Verified by inspection of .github/workflows/deploy-findcare-backend.yml. | tested_passed
TestStep00BuildGate asserts local and dev /health build fields are identical; fails with named builds when they diverge. Smoke catches drift before any cross-env comparison runs. | tested_passed
HF Space Secrets set on dev FindCare/EvaluateCare/SharedServices Spaces. Bootstrap in each main.py/app.py decodes base64-PEM to /tmp/ch_certs on startup. EvaluateCare Dockerfile COPY . . fixed so session_token.py lands in the image. verify result TRUE confirmed on dev via /evaluate/providers response {verified: True}. | tested_passed
_verify_session_identity now extracts the Verified value (YES / VERIFIED / TRUE / OK acceptable) and fails on FAILED or PENDING. Dev with the fix returns VERIFIED; the broken state is now a test failure. | tested_passed
Cell 4-layout assertion passes on local with flex[data-cell] at 18/40/20/22% reactive heights. | tested_passed
Uncheck All now lives inside [data-cell="1"]; assertion passes on local. | tested_passed
All 5 SV labels (Signed token, Nonce, GUID, Origin, Verified) present in right panel; screen arrangement signed off by human 2026-04-17. | tested_passed
_wait_for_verified_resolution polls up to REQ_015_TIMEOUT_S (30s) for Verified to resolve or a Fatal Error splash to render. On an indefinite Pending it raises the REQ-015 VIOLATION message. Integrated at the top of _verify_session_identity. | tested_passed
new
new
2026-04-18 PM fix landed (Claude) — iterated through format/location per human feedback. Final shape: chathealthy_devops_boot.chathealthy_devops_boot._write_req_index() generates a TRANSIENT byte-stream view at .claude/req_index.txt (gitignored via specific-file rule alongside ChatHealthySettings.json). Format is flat pipe-delimited text (NOT structured JSON, NOT Markdown) — one line per requirement: epic_id¦feature_id¦story_id¦req_id¦priority¦status¦approval¦orphan¦requirement_text. Size ~507KB for 2194 reqs (smaller than JSON because no nesting/quoting overhead). _load_brain() calls _write_req_index at end of every boot so the transient refreshes; idempotent via mtime check. CLAUDE.md @-imports the transient from .claude/req_index.txt. Canonical source stays untouched at brain/machine_artifacts/content/agile_backlog.json. BRAIN-RUNTIME-REQ-004 (cache invalidation) is wired into prompt() via _check_brain_freshness — persistent mtime snapshot in ChatHealthySettings.json; any edit to bugs.json/engineering_rules.json/agile_backlog.json between prompts triggers a 'stale context detected' reminder. Research pass: hook additionalContext is hard-capped at 10,000 chars (rules out singleton emission); CLAUDE.md @-imports have no documented cap but the prior 3MB attempt hit an undocumented harness threshold. New transient keeps expanded CLAUDE.md below that threshold. Pytest coverage: TestBugGov010_ReqIndexContextResident (7 tests) plus TestCacheFreshness (6 tests) plus integration tests for the PreToolUse validator hook (4 tests). Full suite: 116/116 pass. | testing
fixing
Fix candidate (a) implemented 2026-04-18: Stop-hook validator scans Claude's turn-1 assistant output for the verbatim mode-prompt substrings ('Select operating mode', '1 = Unattended', '2 = Normal', '3 = Idiot') and returns comply=false/decision=block when any are missing. State machine: boot() sets booted=True and mode_selected=False; prompt_result() enforces the check when booted AND not mode_selected; prompt() clears the gate when the user replies with 1/2/3; session_start/session_end clear both flags. Unit-tested by TestBugGov009_ModePromptEnforcement (11 assertions): verbatim detection, paraphrase rejection, block behavior, allow behavior, no-op after selection, reply capture, session reset. Full test suite 74/74 passes. | testing